## ALL TASKS CLIENT AND GBT
Task No | Project Tasks | Needed for Project? | If Turnkey, Who is Responsible for this sub-task? | Service Provider (Consultant) | Hours allocated | Stage | Cost | Critical For Green Light
1 | Defining the Vision for the Project | YES | CLIENT | Developer | 0 | Pre-construction | 0 | FALSE
2 | Defining "Why the vision and why now" | YES | GBT | Project Manager | 24 | Pre-construction | 3600 | FALSE
3 | Selection of site | YES | CLIENT | Surveyor | 0 | Pre-construction | 0 | FALSE
4 | Preparing the Feasibility / bankability study | YES | CLIENT | Financial Analyst | 0 | Pre-construction | 0 | FALSE
5 | Project value before and after development | YES | CLIENT | Valuer / Appraiser | 0 | Pre-construction | 0 | FALSE
6 | Sector experience | YES | CLIENT | Consultant | 0 | Pre-construction | 0 | FALSE
7 | Development budget preparation | YES | CLIENT | Financial Analyst | 0 | Pre-construction | 0 | FALSE
8 | Identifying and shortlisting financing options | YES | GBT | Financial Analyst | 30 | Pre-construction | 4500 | FALSE
9 | Sourcing best option financing | YES | GBT | Fund Raiser | 60 | Pre-construction | 9000 | FALSE
10 | Develop revenue expectations | YES | GBT | Market Analyst | 20 | Pre-construction | 3000 | FALSE
11 | Planning development timing and deadlines | YES | GBT | Project Manager | 24 | Pre-construction | 3600 | FALSE
12 | Reason for interest in the project | YES | CLIENT | Developer | 0 | Pre-construction | 0 | FALSE
13 | Coordinating with jurisdictional governmental agencies | YES | GBT | Project Manager | 24 | Pre-construction | 3600 | FALSE
14 | Recent property and other relevant surveys | YES | CLIENT | Surveyor | 0 | Pre-construction | 0 | FALSE
15 | Property size where relevant (gross and net developable area) | YES | CLIENT | Surveyor | 0 | Pre-construction | 0 | FALSE
16 | Property condition and value where relevant | YES | CLIENT | Valuer / Appraiser | 0 | Pre-construction | 0 | FALSE
17 | Property zoning where relevant | YES | CLIENT | Planner / Legal Advisor | 0 | Pre-construction | 0 | FALSE
18 | Understanding the Zoning / land use of surrounding properties | YES | GBT | Planner | 8 | Pre-construction | 1200 | FALSE
19 | Identifying physical encroachments | YES | GBT | Surveyor | 8 | Pre-construction | 1200 | FALSE
20 | Identifying existing easements or covenants | YES | GBT | Planner | 8 | Pre-construction | 1200 | FALSE
21 | Identifying right-of-way dedication requirements | YES | GBT | Planner | 8 | Pre-construction | 1200 | FALSE
22 | Engineering design of onsite power and transmission line requirements | YES | GBT | Electrical Engineer | 100 | Pre-construction | 15000 | FALSE
23 | Identifying utility availability or extension needs | YES | GBT | Civil Engineer / Utility Specialist | 48 | Pre-construction | 7200 | FALSE
24 | Defining the target market segment/s | YES | GBT | Market Analyst | 40 | Pre-construction | 6000 | FALSE
25 | Highest and best use of the property | YES | CLIENT | Real Estate Analyst | 0 | Pre-construction | 0 | FALSE
26 | Land title survey check | YES | GBT | Surveyor | 4 | Pre-construction | 600 | FALSE
27 | Walk the property and site photo assessment | YES | GBT | Project Manager | 8 | Pre-construction | 1200 | FALSE
28 | Natural and man-made features analysis | YES | GBT | Environmental Consultant | 16 | Pre-construction | 2400 | FALSE
29 | Environmental, safety, and accessibility considerations | YES | GBT | Environmental Consultant | 16 | Pre-construction | 2400 | FALSE
30 | Conducting a natural resource inventory | YES | GBT | Environmental Consultant | 16 | Pre-construction | 2400 | FALSE
31 | Identifying and undertaking any additional site investigations | YES | GBT | Surveyor / Geotechnical Engineer | 24 | Pre-construction | 3600 | FALSE
32 | Understanding local development attitudes and plans | YES | GBT | Planner / Public Relations Manager | 40 | Pre-construction | 6000 | FALSE
33 | Managing costs incurred during development and construction | YES | GBT | Cost Estimator | 200 | Construction | 30000 | FALSE
34 | Obtaining necessary permits and approvals | YES | GBT | Planner | 24 | Pre-construction | 3600 | FALSE
35 | Construction sequencing | YES | GBT | Project Manager | 48 | Pre-construction | 7200 | FALSE
36 | Initial concept development | YES | GBT | Project Manager | 16 | Pre-construction | 2400 | FALSE
37 | Market and feasibility studies | YES | GBT | Market Analyst | 24 | Pre-construction | 3600 | FALSE
38 | Preliminary financial modeling and projections | YES | GBT | Financial Analyst | 24 | Pre-construction | 3600 | FALSE
39 | Acquisition of land | YES | CLIENT | Real Estate Agent | 0 | Pre-construction | 0 | FALSE
40 | Design concept and master planning | YES | GBT | Project Manager | 200 | Pre-construction | 30000 | FALSE
41 | Architectural and structural designs | YES | GBT | Architect / Engineer | 400 | Pre-construction | 60000 | FALSE
42 | Interior design and branding | YES | GBT | Interior Designer | 48 | Pre-construction | 7200 | FALSE
43 | Landscape design | YES | GBT | Landscape Architect | 100 | Pre-construction | 15000 | FALSE
44 | Engineering studies (structural, MEP, civil) | YES | GBT | Structural Engineer | 200 | Pre-construction | 30000 | FALSE
45 | Environmental impact assessments | YES | GBT | Environmental Consultant | 24 | Pre-construction | 3600 | FALSE
46 | Obtaining necessary development approvals | YES | GBT | Planner | 24 | Pre-construction | 3600 | FALSE
47 | Preparing detailed financial planning and securing financing | YES | GBT | Fund Raiser | 40 | Pre-construction | 6000 | FALSE
48 | Contractor and vendor selection | YES | GBT | Procurement Manager | 24 | Pre-construction | 3600 | FALSE
49 | Construction planning and scheduling | YES | GBT | Project Manager | 48 | Pre-construction | 7200 | FALSE
50 | Infrastructure design and development | YES | GBT | Civil Engineer | 48 | Pre-construction | 7200 | FALSE
51 | Building construction project management | YES | GBT | Project Manager | 1200 | Construction | 180000 | FALSE
52 | Furnishing and interior setup | YES | GBT | Interior Decorator | 200 | Construction | 30000 | FALSE
53 | Operational planning and staff recruitment | YES | CLIENT | Operations Manager | 0 | Post-construction | 0 | FALSE
54 | Marketing and pre-opening activities | YES | CLIENT | Marketing Team | 0 | Post-construction | 0 | FALSE
55 | Official opening and launch | YES | CLIENT | Management | 0 | Post-construction | 0 | FALSE
|  |  |  | Design and Build GBT | 512700 |  | 512700
| Rate per Hour | 150

## GBT ALL TASKS
Project Tasks | Service Provider (Consultant) | Hours allocated | Cost
Defining "Why the vision and why now" | Project Manager | 24 | 3600
Identifying and shortlisting financing options | Financial Analyst | 30 | 4500
Sourcing best option financing | Fund Raiser | 60 | 9000
Develop revenue expectations | Market Analyst | 20 | 3000
Planning development timing and deadlines | Project Manager | 24 | 3600
Coordinating with jurisdictional governmental agencies | Project Manager | 24 | 3600
Understanding the Zoning / land use of surrounding properties | Planner | 8 | 1200
Identifying physical encroachments | Surveyor | 8 | 1200
Identifying existing easements or covenants | Planner | 8 | 1200
Identifying right-of-way dedication requirements | Planner | 8 | 1200
Engineering design of onsite power and transmission line requirements | Electrical Engineer | 100 | 15000
Identifying utility availability or extension needs | Civil Engineer / Utility Specialist | 48 | 7200
Defining the target market segment/s | Market Analyst | 40 | 6000
Land title survey check | Surveyor | 4 | 600
Walk the property and site photo assessment | Project Manager | 8 | 1200
Natural and man-made features analysis | Environmental Consultant | 16 | 2400
Environmental, safety, and accessibility considerations | Environmental Consultant | 16 | 2400
Conducting a natural resource inventory | Environmental Consultant | 16 | 2400
Identifying and undertaking any additional site investigations | Surveyor / Geotechnical Engineer | 24 | 3600
Understanding local development attitudes and plans | Planner / Public Relations Manager | 40 | 6000
Managing costs incurred during development and construction | Cost Estimator | 200 | 30000
Obtaining necessary permits and approvals | Planner | 24 | 3600
Construction sequencing | Project Manager | 48 | 7200
Initial concept development | Project Manager | 16 | 2400
Market and feasibility studies | Market Analyst | 24 | 3600
Preliminary financial modeling and projections | Financial Analyst | 24 | 3600
Design concept and master planning | Project Manager | 200 | 30000
Architectural and structural designs | Architect / Engineer | 400 | 60000
Interior design and branding | Interior Designer | 48 | 7200
Landscape design | Landscape Architect | 100 | 15000
Engineering studies (structural, MEP, civil) | Structural Engineer | 200 | 30000
Environmental impact assessments | Environmental Consultant | 24 | 3600
Obtaining necessary development approvals | Planner | 24 | 3600
Preparing detailed financial planning and securing financing | Fund Raiser | 40 | 6000
Contractor and vendor selection | Procurement Manager | 24 | 3600
Construction planning and scheduling | Project Manager | 48 | 7200
Infrastructure design and development | Civil Engineer | 48 | 7200
Building construction project management | Project Manager | 1200 | 180000
Furnishing and interior setup | Interior Decorator | 200 | 30000
|  | 1970 | 512700
Design and Build GBT | 512700
Pre-construction % | 0% |  | Total GBTA Pre-construction
GBT PM | 238800
GBT FINANCIAL | 23100
GBT OTHER | 250800
TOTAL | 512700

## Traffic Lights Green
Project Tasks | Service Provider (Consultant) | Hours allocated | Cost
Defining "Why the vision and why now" | Project Manager | 24 | 3600
Identifying and shortlisting financing options | Financial Analyst | 30 | 4500
Sourcing best option financing | Fund Raiser | 60 | 9000
Develop revenue expectations | Market Analyst | 20 | 3000
Planning development timing and deadlines | Project Manager | 24 | 3600
Coordinating with jurisdictional governmental agencies | Project Manager | 24 | 3600
Understanding the Zoning / land use of surrounding properties | Planner | 8 | 1200
Identifying physical encroachments | Surveyor | 8 | 1200
Identifying existing easements or covenants | Planner | 8 | 1200
Identifying right-of-way dedication requirements | Planner | 8 | 1200
Engineering design of onsite power and transmission line requirements | Electrical Engineer | 100 | 15000
Identifying utility availability or extension needs | Civil Engineer / Utility Specialist | 48 | 7200
Defining the target market segment/s | Market Analyst | 40 | 6000
Land title survey check | Surveyor | 4 | 600
Walk the property and site photo assessment | Project Manager | 8 | 1200
Natural and man-made features analysis | Environmental Consultant | 16 | 2400
Environmental, safety, and accessibility considerations | Environmental Consultant | 16 | 2400
Conducting a natural resource inventory | Environmental Consultant | 16 | 2400
Identifying and undertaking any additional site investigations | Surveyor / Geotechnical Engineer | 24 | 3600
Understanding local development attitudes and plans | Planner / Public Relations Manager | 40 | 6000
Managing costs incurred during development and construction | Cost Estimator | 200 | 30000
Obtaining necessary permits and approvals | Planner | 24 | 3600
Construction sequencing | Project Manager | 48 | 7200
Initial concept development | Project Manager | 16 | 2400
Market and feasibility studies | Market Analyst | 24 | 3600
Preliminary financial modeling and projections | Financial Analyst | 24 | 3600
Design concept and master planning | Project Manager | 200 | 30000
Architectural and structural designs | Architect / Engineer | 400 | 60000
Interior design and branding | Interior Designer | 48 | 7200
Landscape design | Landscape Architect | 100 | 15000
Engineering studies (structural, MEP, civil) | Structural Engineer | 200 | 30000
Environmental impact assessments | Environmental Consultant | 24 | 3600
Obtaining necessary development approvals | Planner | 24 | 3600
Preparing detailed financial planning and securing financing | Fund Raiser | 40 | 6000
Contractor and vendor selection | Procurement Manager | 24 | 3600
Construction planning and scheduling | Project Manager | 48 | 7200
Infrastructure design and development | Civil Engineer | 48 | 7200
Building construction project management | Project Manager | 1200 | 180000
Furnishing and interior setup | Interior Decorator | 200 | 30000
|  | 1970 | 512700
Design and Build GBT | 512700
Pre-construction % | 0% |  | Total GBTA Pre-construction
GBT PM | 238800
GBT FINANCIAL | 23100
GBT OTHER | 250800
TOTAL | 512700

## GBT PM TASKS
Project Tasks | Service Provider (Consultant) | Hours allocated | Cost
Defining "Why the vision and why now" | Project Manager | 24 | 3600
Planning development timing and deadlines | Project Manager | 24 | 3600
Coordinating with jurisdictional governmental agencies | Project Manager | 24 | 3600
Walk the property and site photo assessment | Project Manager | 8 | 1200
Construction sequencing | Project Manager | 48 | 7200
Initial concept development | Project Manager | 16 | 2400
Design concept and master planning | Project Manager | 200 | 30000
Construction planning and scheduling | Project Manager | 48 | 7200
Building construction project management | Project Manager | 1200 | 180000
|  | 1592 | 238800
Design and Build GBT | 238800
Pre-construction % | 0%

## GBT FINANCIAL TASKS
Project Tasks | Service Provider (Consultant) | Hours allocated | Cost | Project Tasks | Service Provider (Consultant) | Hours allocated | Cost
Identifying and shortlisting financing options | Financial Analyst | 30 | 4500
Sourcing best option financing | Fund Raiser | 60 | 9000
Preliminary financial modeling and projections | Financial Analyst | 24 | 3600
Preparing detailed financial planning and securing financing | Fund Raiser | 40 | 6000
|  | 154 | 23100
Design and Build Financial | 23100
Pre-construction % | 0% |  |  |  | Total GBTA Pre-construction |  | #REF!

## GBT OTHER TASKS
Project Tasks | Service Provider (Consultant) | Hours allocated | Cost
Develop revenue expectations | Market Analyst | 20 | 3000
Understanding the Zoning / land use of surrounding properties | Planner | 8 | 1200
Identifying physical encroachments | Surveyor | 8 | 1200
Identifying existing easements or covenants | Planner | 8 | 1200
Identifying right-of-way dedication requirements | Planner | 8 | 1200
Engineering design of onsite power and transmission line requirements | Electrical Engineer | 100 | 15000
Identifying utility availability or extension needs | Civil Engineer / Utility Specialist | 48 | 7200
Defining the target market segment/s | Market Analyst | 40 | 6000
Land title survey check | Surveyor | 4 | 600
Natural and man-made features analysis | Environmental Consultant | 16 | 2400
Environmental, safety, and accessibility considerations | Environmental Consultant | 16 | 2400
Conducting a natural resource inventory | Environmental Consultant | 16 | 2400
Identifying and undertaking any additional site investigations | Surveyor / Geotechnical Engineer | 24 | 3600
Understanding local development attitudes and plans | Planner / Public Relations Manager | 40 | 6000
Managing costs incurred during development and construction | Cost Estimator | 200 | 30000
Obtaining necessary permits and approvals | Planner | 24 | 3600
Market and feasibility studies | Market Analyst | 24 | 3600
Architectural and structural designs | Architect / Engineer | 400 | 60000
Interior design and branding | Interior Designer | 48 | 7200
Landscape design | Landscape Architect | 100 | 15000
Engineering studies (structural, MEP, civil) | Structural Engineer | 200 | 30000
Environmental impact assessments | Environmental Consultant | 24 | 3600
Obtaining necessary development approvals | Planner | 24 | 3600
Contractor and vendor selection | Procurement Manager | 24 | 3600
Infrastructure design and development | Civil Engineer | 48 | 7200
Furnishing and interior setup | Interior Decorator | 200 | 30000
|  | 292 | 250800
Design and Build GBT Other | 250800 |  | GBTA % Rate
Pre-construction % | 48.92% |  | Total GBTA Pre-construction